FactoryOS

Flexible Packaging Manufacturing ERP

Implementation Proposal — Timeline & Budget Estimate

Prepared for: Yuva Polyprint and Packaging Industries

Prepared by: Abhi

August 2026

# 1. Executive Summary

Yuva Polyprint is a flexible packaging and laminated packaging manufacturer producing stand-up pouches, center-sealed and three-side-seal pouches, spout pouches, side-gusset pouches, shrink and stretch sleeves, roll-fed labels, lid laminates, laminated rolls, shrink wrap, and industrial bags — serving customers across food, dairy, pharma, personal care, beverage, chemicals, paints, and apparel. Production runs through four core operations — Rotogravure Printing, Lamination, Slitting, and Pouch Making — with multiple jobs active simultaneously across different stages at any time.

This is not a generic small-business ERP. It requires a configurable Product Master where every product defines its own required operations, a dedicated Design & Cylinder Management module for Rotogravure printing, dynamic rate-based quotation, full job-level traceability, and estimated-vs-actual costing to identify hidden margin loss. A clickable wireframe covering all 20 screens of this system has already been built and reviewed — this proposal covers turning that validated design into a working, production-grade system.

TOTAL PROJECT TIMELINE 8 – 12 months (35 – 50 weeks)

TOTAL PROJECT INVESTMENT ₹49,00,000 – ₹74,00,000

UPPER BOUND (worst case, full scope, all contingency used) 12 months · ₹74,00,000

# 2. Project Understanding

Confirmed production stages:

- Rotogravure Printing

- Lamination

- Slitting

- Pouch Making

Why this system is more complex than a standard manufacturing ERP:

- Multiple jobs run concurrently across different stages — the system must model concurrent, non-linear production, not a single fixed line.

- Every product defines its own workflow. A laminated roll skips Pouch Making; a roll-fed label skips Lamination; an industrial bag skips Printing.

- Rotogravure printing depends on engraved cylinders per design — cylinder ownership, storage, cost, damage, and reuse must be tracked.

- Customers span 10+ industries with materially different material structures, layers, and quality requirements — the quotation engine cannot be built for one product type.

- Every order needs to be traceable end-to-end: customer → design/cylinder → materials → stage-wise production → waste → quality → cost → dispatch.

# 3. Scope of Work — Modules

## Commercial

- Customer & Requirement capture

- Dynamic rate-based Quotation engine

- Order intake & conversion tracking

## Product & Design

- Product Master (configurable categories, types, required operations)

- Design & Cylinder Management (ownership, storage, cost, reuse, history)

## Production

- Planning & Material Requirement

- Production / Job Card (multi-stage, concurrent-order tracking)

- Roll traceability (raw → printed → laminated → slit)

## Materials

- Inventory (raw materials, WIP, finished goods)

- Warehouse (zones, locations, stock movement)

- Purchase & Supplier Management (rate history, POs)

## Control

- Quality Management (stage-wise checks, pass/fail, inspector)

- Waste Tracking (by stage, by reason)

## Resources

- Machine Master & live monitoring

- Employee / Operator management

- Simplified shop-floor Operator interface

- Maintenance

## Commercial Close-out

- Costing — Estimated vs Actual

- Profitability by customer / product

- Dispatch & Delivery tracking

## Platform

- Role-based access (Owner, Manager, Supervisor, Warehouse, Operator, Quality, Admin)

- Dashboards & Reports

- Audit trail & history

# 4. Delivery Approach

The build follows the same priority order validated with the client:

- Priority 1 — Confirm real Job Card, costing sheets, and quotation formats before Phase 2 begins (critical path).

- Priority 2 — Dynamic rate + automated quotation engine.

- Priority 3 — Configurable Product & Production workflow.

- Priority 4 — Job tracking across concurrent orders.

- Priority 5 — Inventory, material consumption & waste.

- Priority 6 — Actual vs estimated costing.

- Priority 7 — Machine & operator tracking.

- Priority 8 — Purchase / supplier management.

- Priority 9 — Dispatch & delivery tracking.

- Priority 10 — Quality management.

Recommended stack: responsive web application (desktop for office/management roles, tablet-friendly for shop floor), role-based authentication, relational database, cloud hosting with staged dev/UAT/production environments. Final stack confirmed at architecture sign-off in Phase 1.

# 5. Phased Implementation Plan

| Phase | Key Deliverables | Duration — Lower | Duration — Upper |
| --- | --- | --- | --- |
| 1 | Discovery, requirement sign-off, solution architecture, UX refinement of the approved wireframe | 3 weeks | 4 weeks |
| 2 | Platform foundation (auth, roles, admin), Product Master, Customer & Quotation engine | 6 weeks | 8 weeks |
| 3 | Orders, Planning / Material Requirement, Design & Cylinder Management | 4 weeks | 6 weeks |
| 4 | Production / Job Card (concurrent multi-stage tracking, roll traceability), Machine & Operator tracking, shop-floor Operator UI | 7 weeks | 9 weeks |
| 5 | Inventory, Warehouse, Purchase & Supplier Management | 4 weeks | 6 weeks |
| 6 | Quality Management, Waste Tracking, Estimated-vs-Actual Costing, Profitability | 4 weeks | 6 weeks |
| 7 | Dispatch & Delivery, Reports & Dashboards | 3 weeks | 5 weeks |
| 8 | Integration testing, UAT, training, deployment & hypercare | 4 weeks | 6 weeks |

|  | Lower Bound | Upper Bound |
| --- | --- | --- |
| Total Duration | 35 weeks (≈ 8 months) | 50 weeks (≈ 12 months) |

Phase durations assume a dedicated core team (Section 6) working in parallel across sub-workstreams; the ranges reflect realistic variance from requirement clarity, data availability, and review turnaround — not scope reduction.

# 6. Team & Effort Estimate

| Role | Engagement | Monthly Rate (₹) | Notes |
| --- | --- | --- | --- |
| Project Manager / BA | ~50% | 1,00,000 | Requirement sign-off, client liaison |
| Solution Architect | ~35% | 1,60,000 | Architecture, code review, tech decisions |
| Backend Developer (× 2) | 100% | 90,000 each | Core APIs, workflow engine, integrations |
| Frontend Developer (× 2) | 100% | 80,000 each | Web app, shop-floor UI |
| QA Engineer | ~70% | 60,000 | Ramps up from Phase 3 onward |
| UI/UX Designer | ~40% | 70,000 | Front-loaded — wireframe already complete |
| DevOps Engineer | ~20% | 80,000 | Environments, CI/CD, deployment |

| Blended Team Cost | ≈ ₹5,32,000 / month (≈ ₹1,22,900 / week) |
| --- | --- |

# 7. Detailed Budget Breakdown

## 7.1 Development Cost by Phase

| Phase | Scope | Lower Bound (₹) | Upper Bound (₹) |
| --- | --- | --- | --- |
| 1 | Discovery, Architecture & UX Refinement | 3,70,000 | 4,90,000 |
| 2 | Platform Foundation, Product Master, Quotation Engine | 7,40,000 | 9,80,000 |
| 3 | Orders, Planning, Design & Cylinder Management | 4,90,000 | 7,40,000 |
| 4 | Production / Job Card, Machine & Operator Tracking, Shop-floor UI | 8,60,000 | 11,10,000 |
| 5 | Inventory, Warehouse, Purchase & Supplier | 4,90,000 | 7,40,000 |
| 6 | Quality, Waste, Costing & Profitability | 4,90,000 | 7,40,000 |
| 7 | Dispatch, Reports & Dashboards | 3,70,000 | 6,20,000 |
| 8 | Integration Testing, UAT, Training, Deployment | 4,90,000 | 7,40,000 |

|  | Lower Bound (₹) | Upper Bound (₹) |
| --- | --- | --- |
| Development Subtotal | 43,00,000 | 61,60,000 |

## 7.2 Additional Costs

| Item | Lower Bound (₹) | Upper Bound (₹) |
| --- | --- | --- |
| Infrastructure & tooling (dev/staging/prod cloud, CI/CD, licenses, SSL/domain) | 1,50,000 | 3,00,000 |
| Contingency (10% lower / 15% upper — scope refinement buffer) | 4,45,000 | 9,69,000 |

TOTAL PROJECT INVESTMENT ₹49,00,000 (Lower) — ₹74,00,000 (Upper Bound)

Recurring post-launch costs (not included above): cloud hosting & maintenance ₹25,000 – ₹60,000/month depending on scale; optional Annual Maintenance Contract at 18–20% of project cost/year covers bug fixes, minor enhancements, and support SLAs.

# 8. Payment Milestones

| % | Milestone |
| --- | --- |
| 15% | On signing / project kickoff |
| 20% | Phase 1–2 sign-off (Foundation + Commercial Engine) |
| 25% | Phase 3–4 sign-off (Production / Job Card core) |
| 20% | Phase 5–6 sign-off (Materials + Costing) |
| 15% | UAT sign-off |
| 5% | Go-live & hypercare completion |

# 9. Assumptions & Exclusions

- Client provides existing Job Card formats, costing sheets, quotation examples, and inventory data within the first 2 weeks — this is on the critical path (Priority 1) and any delay shifts the timeline directly.

- One round of UI refinement is included per module beyond the approved wireframe; additional design iterations are billed separately.

- Responsive web application for desktop and tablet is included; native iOS/Android apps are excluded from this scope.

- Integration with third-party accounting software (e.g. Tally) is excluded unless separately scoped.

- Cylinder / roll tracking assumes standard barcode or QR scanning via commodity USB/Bluetooth scanners; custom hardware integration is excluded.

- Data migration covers master data only (products, customers, materials, machines); historical transaction migration is a separately scoped effort.

- System sized for up to 50 concurrent users; higher scale may require additional infrastructure planning and cost.

- Hosting, domain, and third-party service costs (SMS/WhatsApp notifications, backups) beyond the build-phase allowance are billed at actuals post-launch.

# 10. Risks & Mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Delay in receiving real Job Card / costing data | Costing engine cannot be finalized without it — this is Priority 1 | Kickoff workshop dedicated to data collection before Phase 2 starts |
| Requirement volatility given configurable-workflow scope | Scope creep risk across Product Master and workflow engine | Phased sign-offs; change requests tracked against contingency budget |
| Product/customer diversity increases QA surface | More edge cases across 10+ industries and 14+ product types | Representative product set defined and tested per category, not exhaustively per SKU |
| Cylinder / design historical data incompleteness | Design & Cylinder module accuracy depends on existing records | Start with active designs/cylinders; backfill history incrementally |

# 11. Next Steps

- Review and sign off this proposal.

- Kickoff workshop — walk through the approved wireframe screen by screen with all stakeholder roles.

- Collect real Job Card, costing sheets, and quotation formats (Priority 1 data).

- Begin Phase 1 — Discovery, Architecture & UX Refinement.

This proposal is valid for 30 days from the date above. All figures are in Indian Rupees (₹) and exclude applicable taxes (GST).